## Ramnagara DC meeting 1
KARNATAKA ROAD DEVELOPMENT CORPORATION LTD.
DETAILS OF ROADS AROUND BENGALURU BIDADI TO ANEKAL
(Amount in Crore)
Sl.No | Package No | Name of the work | Nature of work | Length (In km) | Total project cost (In crore) | Contract amount exckluding GST | Tentative LA cost | Micelleanous and ultility shifting | Land Acquisition | Tree cutting after demarkation of ROW |  | Electrical Line shifting | Tank Bund Details​ | Tele poles | Traffic poles | Transformers | UD units | Physical status | Agency | Tender Premium | Expected GST (12% of Quoted) | Total | Mobilisation advance
1 | 2 | 3 | 4 | 5 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | [5 empty] | 8 |  |  | 11 | 12=10+11 | 13
1 | 3A | Kanchugaranahalli to Jigani via Harohalli and Urgandoddi (km 0+000 to km 33+200) and section of road from BM road junction to Coca cola factory (km 0+000 to km 3+000) of Bidadi-Harohalli road | Road | 33.2 | 199.29 | 135.08 | 37.22 | 40.67 | *Harohalli By pass revised alignment is approved by Technical Committee accordingly LA plan revised and submitted to Government for approval for preliminary notification | Kanakapura RFO Anekal RFO | Ch. 0.00 to 17.200 Km total no of trees 652 ACF (Ramnagagr ACF) * Tree cutting permission recieved , charges to be remitted to Forest Dept From contractor to issue the Work order from DCF (R) *Ch. 23.00 to 33.20 km No of trees 184. Tree cutting permission awaited, the proposal is to be placed before the committee. | AEE, Harohalli sub division (intimation letter recieved & amount paid of Rs. 17,93,600 + 62,587 ) work order issued from BESCOM dated 08-11-2019 and AEE, Jigani sub division (intimation letter recieved & amount paid of Rs. 17,93,600 + 19, 258) work order issued from BESCOM dated 08-11-2019 Electrical work started. | Nil |  |  |  |  | *Harohalli By pass revised alignment is approved by Technical Committee accordingly LA plan revised and submitted to Government for approval, Accordingly Notice will be issued to the land owner. *Krishnanadoddi By-pass alignment fixed. SIA to be initiated * Except By-pass fixing of ROW is completed. * Electrical estimate recieved from BESCOM, supervision charges paid. work order issued dated:08-11-2019 from BESCOM. MOU between BESCOM & KRDCL to be excuted. Work will be started shortly. * The proposal for 4Lane from Kanchagaranahalli to Harohalli (0.00 to 4.50 km) as per the instructions of MD, KRDCL during site visit. topo survey completed, LA is in progress, * Public are objecting to take up the drain work at the edge of the Carrageway instead they are asking to execute at boundary of the project stretch, accordingly action is initiated. * proposal submitted for approval of quarry to DC Ramnagara | TIRUPATHI REDDY DEVARAPALLI (K N R CONSTRUCTIONS LIMITED) | 9.269% | 4.8804 | 45.5504 | 2.2775
2 | 3 B | Bannerghatta on SH-87 to Besthamanahalli on SH-35 (including Anekal bypass, Grade separator across Chandapura road and ROB across railway line) via Jigani, Haragadde and Indalwadi (km 0+000 to km 22+980) | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 129.89 | 34.19 | 40.13 | Anekal By-pass alignment passes through existing Karpura kere water body, hence it attracts environamental issues. MD instructed during site visit dated 07-11-2019 to realign the Bypass with alternative proposals wthin a week. | Anekal RFO, | Total: 520 No's LHS - Ch.0+000 toCh.18+180 =319 No's RHS - Ch. 0+000 toCh. 17+000 = 201 No's * Tree cutting awaited, letter sent dated: 01/04/2019 & Proposal will be placed before committee on 19-11-2019 for decission | AEE, Jigni sub division Ch. 0.000 to 13.600 (intimation letter recieved & amount paid of Rs. 17,93,600 SC ) dated : 12-10-2019 and MOU executed between BESCOM & KRDCL, dated: 07-11-2019, work order awaited from BESCOM. AEE, Anekal sub division Ch. 13.600 to Ch. 18.250 (intimation letter recieved & amount paid of Rs. 17,93,600 SC ) dated : 12-10-2019 and MOU executed between BESCOM & KRDCL, dated: 07-11-2019, work order awaited from BESCOM. (Anekal bypass 18.25 to 22.972 pending) | I. Anekal Doddakare bund length = 1.400 km, Ch. 16+900 to Ch. 18+300 – LA required: 12m for widening along LHS of the Lake II. Karapura Kare inside the lake for a length of 0.500 km, Ch.21+450 to Ch.21+950 – LA required: 24m |  |  |  |  | * Except By-pass fixing of ROW is completed * Site office, Laboratory & batch mix plant, construction work is in progress. | KMV PRASAD RAO (KMV PROJECTS LIMITED) | 17.37% | 4.8156 | 44.9456 | 2.2473
| Total for 10 Packages: |  |  |  | 393.4 | 264.97 | 71.41 | 80.8 | [12 empty] | 9.696 | 90.496 | 4.5248

## Ramnagara DC meeting (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LTD.
DETAILS OF ROADS AROUND BENGALURU BIDADI TO ANEKAL
Total Length of Road 155 Km, Project cost Rs.2095 Crore
(Amount in Crore)
Sl.No | Package No | Indent No. | Name of the work | Nature of work | Length (In km) | Total project cost (In crore) | Contract amount exckluding GST | Tentative LA cost | Micelleanous and ultility shifting | Land Acquisition | Tree cutting as per DFR | Tree cutting after demarkation of ROW |  | Water supply pipe line shifting | Electrical Line shifting | Tank Bund Details​ | Tele poles | Traffic poles | Transformers | UD units | Physical status | Agency | Tender Premium | Expected GST (12% of Quoted) | Total | Mobilisation advance
1 | 2 | 3 | 3 | 4 | 5 | 7 | 8 | 9 | 10 | 11 | 7 | 12 |  |  | 13 | [5 empty] | 8 |  |  | 11 | 12=10+11 | 13
1 | 3A | KRDCL/2017-18/RD /WORK_INDENT317 | Kanchugaranahalli to Jigani via Harohalli and Urgandoddi (km 0+000 to km 33+200) and section of road from BM road junction to Coca cola factory (km 0+000 to km 3+000) of Bidadi-Harohalli road | Road | 33.2 | 199.29 | 135.08 | 37.22 | 40.67 | *Harohalli By pass revised alignment is approved by Technical Committee accordingly LA plan revised and submitted to Government for approval for preliminary notification | 392 Tree cutting proposals to be sent to concerned DFO. | Kanakapura RFO Anekal RFO | Ch. 0.00 to 17.200 Km total no of trees 652 ACF (Ramnagagr ACF) * Tree cutting permission recieved , charges to be remitted to Forest Dept From contractor to issue the Work order from DCF (R) *Ch. 23.00 to 33.20 km No of trees 184. Tree cutting permission awaited, the proposal is to be placed before the committee. | water supply line identified, estimate under preparation by RWS Dept. | AEE, Harohalli sub division (intimation letter recieved & amount paid of Rs. 17,93,600 + 62,587 ) work order issued from BESCOM dated:08-11-2019 and AEE, Jigani sub division (intimation letter recieved & amount paid of Rs. 17,93,600 + 19, 258) work order issued from BESCOM dated 08-11-2019 Electrical work started. | Nil |  |  |  |  | *Harohalli By pass revised alignment is approved by Technical Committee accordingly LA plan revised and submitted to Government for approval, Accordingly Notice will be issued to the land owner. *Krishnanadoddi By-pass alignment fixed. SIA to be initiated * Except By-pass fixing of ROW is completed. * Electrical estimate recieved from BESCOM, supervision charges paid. work order issued dated:08-11-2019 from BESCOM. MOU between BESCOM & KRDCL to be excuted. Work will be started shortly. * The proposal for 4Lane from Kanchagaranahalli to Harohalli (0.00 to 4.50 km) as per the instructions of MD, KRDCL during site visit. topo survey completed, LA is in progress, * Public are objecting to take up the drain work at the edge of the Carrageway instead they are asking to execute at boundary of the project stretch, accordingly action is initiated. * proposal submitted for approval of quarry to DC Ramnagara | TIRUPATHI REDDY DEVARAPALLI (K N R CONSTRUCTIONS LIMITED) | 9.269% | 4.8804 | 45.5504 | 2.2775
2 | 3 B | KRDCL/2017-18/RD /WORK_INDENT318 | Bannerghatta on SH-87 to Besthamanahalli on SH-35 (including Anekal bypass, Grade separator across Chandapura road and ROB across railway line) via Jigani, Haragadde and Indalwadi (km 0+000 to km 22+980) | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 129.89 | 34.19 | 40.13 | Anekal By-pass alignment passes through existing Karpura kere water body, hence it attracts environamental issues. MD instructed during site visit dated 07-11-2019 to realign the Bypass with alternative proposals wthin a week. | 104 Tree cutting proposals to be sent to concerned DFO. | Anekal RFO, | Total: 520 No's LHS - Ch.0+000 toCh.18+180 =319 No's RHS - Ch. 0+000 toCh. 17+000 = 201 No's * Tree cutting awaited, letter sent dated: 01/04/2019 & Proposal will be placed before committee on 19-11-2019 for decission | water supply line identified, estimate under preparation by RWS Dept. | AEE, Jigni sub division Ch. 0.000 to 13.600 (intimation letter recieved & amount paid of Rs. 17,93,600 SC ) dated : 12-10-2019 and MOU executed between BESCOM & KRDCL, dated: 07-11-2019, work order awaited from BESCOM. AEE, Anekal sub division Ch. 13.600 to Ch. 18.250 (intimation letter recieved & amount paid of Rs. 17,93,600 SC ) dated : 12-10-2019 and MOU executed between BESCOM & KRDCL, dated: 07-11-2019, work order awaited from BESCOM. (Anekal bypass 18.25 to 22.972 pending) | I. Anekal Doddakare bund length = 1.400 km,Ch. 16+900 to Ch. 18+300 LA required: 12m for widening along LHS of the Lake II. Karapura Kare inside the lake for a length of 0.500 km, Ch.21+450 to Ch.21+950 – LA required: 24m |  |  |  |  | * Except By-pass fixing of ROW is completed * Site office, Laboratory & batch mix plant, construction work is in progress. | KMV PRASAD RAO (KMV PROJECTS LIMITED) | 17.37% | 4.8156 | 44.9456 | 2.2473
| Total for 10 Packages: |  |  |  |  | 393.4 | 264.97 | 71.41 | 80.8 | [14 empty] | 9.696 | 90.496 | 4.5248

## Nature of work (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LIMITED
Development of Bengaluru surrounding Roads
Sl No | District | Division | Name of Work | Length in km/Structure in No. | Major Junctions | Minor Junctions | Major Bridge | Minor Bridges | Culverts | Carriageway Configuration | Pavement Type | No. of Villages / Town | No. of Bus bays | No. Of Bye pass | Period of completion
1 | Bengaluru | Bengaluru | Package-1: Development of Road from Hoskote Budigere Cross (NH-4) to Kempegowda International Airport road via Budigere-Singahalli and Mylanahalli (from Km 0+00 to 21+500) in Bangalore Urban/Rural District. | 20.11 | 4 | 48 |  | 2 | 38 | 4L and 6L | Flexible | 10 | 13 | 1 | 30 months
2 | Bengaluru | Bengaluru | Package-2A: Development of Road from Nelamangala from NH-4 to Madhure on SH-74 via Chikkamadhure (from Km 0+00 to 15+250) in Bangalore. | 14.16 | 2 | 38 |  | 3 | 20 | 4L | Flexible | 7 | 4 | 0 | 30 months
3 | Bengaluru | Bengaluru | Package-2B: Development of Road from Madhure on SH 74 to Devanahalli road (EMM VEE Solars on NH 7) via Rajanakunte and Thimmasandra (from Km 15+250 to 39+240). in Bangalore | 22.42 | 1 | 52 |  | 2 | 37 | 4L | Flexible | 25 | 7 | 0 | 30 months
4 | Bengaluru | Bengaluru | Package-2C (Call-2): Construction of RUB at Basavanahalli Railway Crossing near Nelamangala Railway station (km 0+800) on SH 74 and ROB at Gollahalli Railway crossing (km 6+330) on SH 74 in Bangalore. | 1.09 | [5 empty] | RUB 2L and ROB 4L |  |  |  |  | 30 months
5 | Bengaluru | Bengaluru | Package-2D: Construction of ROB at Rajanakunte for crossing Railway line & SH 9 (Km 32+185) and ROB at Railway crossing at Narayanapura (Km 36+840) on MDR in Bangalore. | 1.18 | [5 empty] | ROB1 2L and ROB2 4L |  |  |  |  | 30 months
6 | Bengaluru Ramanagaram | Bengaluru | Package-3A: Development of road from Kanchugaranahalli to Jigani via Harohalli and Urgandoddi (km 0+000 to km 33+200) and section of road from BM road junction to Coca cola factory (km 0+000 to km 3+000) of Bidadi-Harohalli road in Bengaluru | 33.401 | 7 |  |  | 6 | 53 | 2L and 4L | Flexible | 11 | 16 | 2 | 30 months
7 | Bengaluru | Bengaluru | Package-3B: Development of road from Bannerghatta on SH-87 to Besthamanahalli on SH-35 (including Anekal bypass, Grade separator across Chandapura road and ROB across railway line) via Jigani, Haragadde and Indalwadi (km 0+000 to km 22+980) in Bengaluru | 22.98 | 8 |  |  | 1 | 24 | 4L and 6L | Flexible | 11 | 26 | 1 | 30 months
8 | Bengaluru | Bengaluru | Package-4A: Development of road from Besthamanahalli (Anekal) on SH-35 to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield length 39.280 (km 0+000 to km 42+600) (excluding elevated corridor, Grade separator and ROB) in Bengaluru | 39.06 | 7 |  | 1 | 8 | 34 | 2L, 4L and 6L | Flexible | 13 | 18 | 0 | 30 months
9 | Bengaluru | Bengaluru | Package-4B (Call-2): Construction of Elevated Corridor at Varthur village (1.300 km) in Bengaluru | 1.34 | [5 empty] | 4L |  |  |  |  | 30 months
10 | Bengaluru | Bengaluru | Package-4C: Construction of Grade Separators at Tally Junction, Dommasandra Junction, Varthur Kodi Junction and ROB at Kadugodi in Bangalore | 2.26 | 4 | [9 empty] | 30 months
Total |  |  |  | 158.001 | 33 | 138 | 1 | 22 | 206 | 0 | 0 | 77 | 84 | 4 | 0
-0.001

## Final Abstract in Cr (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LIMITED
Development of Bengaluru surrounding Roads
Sl No | District | Division | Name of Work | Start | End | Leftout | Length in km | Length in km/Structure in No. | Total Estimated project cost | Contract Amount in Crore | Date of Agreement | Start Date (Site handed over on) | Due date of Completion | Contractor | Supervision Consultant
1 | Bengaluru | Bengaluru | Package-1: Development of Road from Hoskote Budigere Cross (NH-4) to Kempegowda International Airport road via Budigere-Singahalli and Mylanahalli (from Km 0+00 to 21+500) in Bangalore Urban/Rural District. | 0 | 20.11 |  | 20.11 | 20.11 | 254 | 137.5189 | 2019-06-19 | 2019-07-01 | 2021-12-30 | M/s. S.R.C INFRA DEVELOPERS Pvt.Ltd. Bengaluru | M/s. Niketan Consultants, Bengaluru
2 | Bengaluru | Bengaluru | Package-2A: Development of Road from Nelamangala from NH-4 to Madhure on SH-74 via Chikkamadhure (from Km 0+00 to 15+250) in Bangalore. | 0 | 15.25 |  | 15.25 | 15.25 | 232.55 | 155.6938 | 2019-03-08 | 2019-04-29 | 2021-10-28 | M/s. STAR INFRATECH, Bengaluru | M/s. Infra Support Engineering Consultants Pvt. Ltd. Bengaluru
3 | Bengaluru | Bengaluru | Package-2B: Development of Road from Madhure on SH 74 to Devanahalli road (EMM VEE Solars on NH 7) via Rajanakunte and Thimmasandra (from Km 15+250 to 39+240). in Bangalore | 15.25 | 39.262 |  | 24.012 | 23.99 | 316.3 | 169.8099 | 2019-03-08 | 2019-06-20 | 2021-12-19 | M/s. BSR INFRATECH INDIA LIMITED, Bengaluru | M/s. Infra Support Engineering Consultants Pvt. Ltd. Bengaluru
4 | Bengaluru | Bengaluru | Package-2C (Call-2): Construction of RUB at Basavanahalli Railway Crossing near Nelamangala Railway station (km 0+800) on SH 74 and ROB at Gollahalli Railway crossing (km 6+330) on SH 74 in Bangalore. |  |  |  | 0 | 1 RUB 1 ROB | 68.83 | 47.885 | 2019-03-08 | 2019-05-06 | 2021-11-05 | M/s. KMV PROJECTS LIMITED, Hyderabad | Tender Reinvited
5 | Bengaluru | Bengaluru | Package-2D: Construction of ROB at Rajanakunte for crossing Railway line & SH 9 (Km 32+185) and ROB at Railway crossing at Narayanapura (Km 36+840) on MDR in Bangalore. |  |  |  | 0 | 2 ROB | 97.28 | 54.4803 | 2019-03-08 | 2019-04-04 | 2021-10-03 | M/s. P J B ENGINEERS PRIVATE LIMITED, Bengaluru
6 | Bengaluru Ramanagaram | Bengaluru | Package-3A: Development of road from Kanchugaranahalli to Jigani via Harohalli and Urgandoddi (km 0+000 to km 33+200) and section of road from BM road junction to Coca cola factory (km 0+000 to km 3+000) of Bidadi-Harohalli road in Bengaluru | 0 | 33.2 |  | 33.2 | 33.2 | 199.29 | 135.0843 | 2019-03-08 | 2019-06-21 | 2021-12-20 | M/s. K N R CONSTRUCTIONS LIMITED, Hyderabad | M/s. Apt Consulting Engineering Services, Bengaluru
7 | Bengaluru | Bengaluru | Package-3B: Development of road from Bannerghatta on SH-87 to Besthamanahalli on SH-35 (including Anekal bypass, Grade separator across Chandapura road and ROB across railway line) via Jigani, Haragadde and Indalwadi (km 0+000 to km 22+980) in Bengaluru | 0 | 24.09 |  | 24.09 | Road 22.98km + 1 Grade seperater + 1 ROB | 194.11 | 129.8922 | 2019-03-08 | 2019-05-06 | 2021-11-05 | M/s. KMV PROJECTS LIMITED, Hyderabad | M/s. COS Consultancy Services, Madurai
8 | Bengaluru | Bengaluru | Package-4A: Development of road from Besthamanahalli (Anekal) on SH-35 to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield length 39.280 (km 0+000 to km 42+600) (excluding elevated corridor, Grade separator and ROB) in Bengaluru | 0 | 21.5 |  | 21.5 | 39.28 | 312.08 | 182.2297 | 2019-03-08 | 2019-06-15 | 2021-12-14 | M/s. RNS INFRASTRUCTURE LIMITED, Bengaluru | M/s. Apt Consulting Engineering Services, Bengaluru
9 | Bengaluru | Bengaluru | Package-4B (Call-2): Construction of Elevated Corridor at Varthur village (1.300 km) in Bengaluru | 0 | 21.5 |  | 21.5 | 1.30 Elevated Road | 286.62 | 163.18 | 2019-03-08 | 2019-05-20 | 2021-11-19 | M/s. NAGABHUSHANAM AND CO. Hyderabad | M/s. Mukesh & Associates , Salem
10 | Bengaluru | Bengaluru | Package-4C: Construction of Grade Separators at Tally Junction, Dommasandra Junction, Varthur Kodi Junction and ROB at Kadugodi in Bangalore | 0 | 21.5 |  | 21.5 | 3 Grade seperater 1 ROB | 133.94 | 65.1718 | 2019-03-08 | 2019-07-03 | 2022-01-04 | M/s. P J B ENGINEERS PRIVATE LIMITED, Bengaluru | M/s. C. V. Kand Consultants Pvt. Ltd. Bengaluru
Total | [8 empty] | 2095 | 1240.9459

## Financial milestones (F) (hidden)
DETAILS OF ROADS AROUND BENGALURU PROPOSED FOR DEVELOPMENT (IN 10 PACKAGES )
Total Length of Road 155 Km, Project cost Rs.2095 Crore Total Packages 10 Road Packages 5 Structure Packages 4 Road & StructurePackages 1
(Amount in Crore)
Sl.No | Package No | Name of the work | Nature of work | Length (In km) | Total project cost (In crore) | Constrcuction cost | Amount put to tender (In crore) | Land acquisition (In acre) | Tentative Financial Mile Stones yearwise cost in crore |  |  |  | Total project cost (In crore) | Tentative Financial Mile Stones for Construction cost in crore |  |  |  | Total construction cost | Present Status
[9 empty] | 2018-19 | 2019-20 | 2020-21 | 2021-22 |  | 3 months | 12 months | 12 months | 3 months
1 | 1 | Hoskote Budigere cross (NH-4) to Kempegowda international airport road via Budigere- Singahalli and Mylanahalli in Bengaluru | Road | 20.11 | 254 | 169.73 | 137.33 | 19.63 | 18 | 77.66 | 116.27 | 42.07 | 254 | 12.04 | 51.87 | 77.7 | 28.12 | 169.73 | Financial bid placed before the board for approval
2 | 2A | Nelamangala from NH-4 to Madhure on SH 74 via Chikkamadhure from 0+00 to 15+250) in Bengaluru | Road | 15.25 | 232.55 | 190.05 | 153.8 | 5.93 | 17.82 | 90.47 | 98.59 | 25.67 | 232.55 | 11.78 | 59.82 | 65.21 | 16.99 | 153.8 | Financial bid placed before the board for approval
3 | 2 B | Madhure on SH 74 to Devanahalli road (EMM VEE Solars on NH 7) via Rajanukunte and Thimmasandra (from km 15+250 to 39+240) in Bengaluru | Road | 23.99 | 316.3 | 210.54 | 170.4 | 14.38 | 24.23 | 123.05 | 134.09 | 34.93 | 316.3 | 13.05 | 66.3 | 72.23 | 18.82 | 170.4 | Financial bid placed before the board for approval
4 | 2 C | Construction of RUB at Basavanahalli Railway crossing near Nelamangala railway station (km 0+800) on SH 74 and ROB at Gollahalli railway crossing (km 6+300) on SH 74 in Bengaluru | RUB/ ROB | 1 RUB 1 ROB | 68.83 | 61.15 | 47.49 | 1.95 |  | 17.8 | 31.88 | 19.15 | 68.83 | 3.36 | 14.52 | 21.74 | 7.87 | 47.49 | Retendered, Last Date of reciept: 05-02-2019
5 | 2 D | Construction of ROB at Rajanakunte for crossing railway line & SH 9 (km 32+185) and ROB at railway crossing at Narayanapura (km 36+840) on MDR in Bengaluru | ROB | 2 ROB | 97.28 | 70.34 | 55 | 2.95 | 6.33 | 21.61 | 47.84 | 21.5 | 97.28 | 3.59 | 12.23 | 27.03 | 12.15 | 55 | Financial bid placed before the board for approval
6 | 3A | Kanchugaranahalli to Jigani via Harohalli and Urgandoddi (km 0+000 to km 33+200) and section of road from BM road junction to Coca cola factory (km 0+000 to km 3+000) of Bidadi-Harohalli road in Bengaluru | Road | 33.2 | 199.29 | 121.4 | 140.72 | 30.38 | 16 | 76.61 | 84.68 | 22 | 199.29 | 14.072 | 70.36 | 56.288 |  | 140.72 | Financial bid placed before the board for approval
7 | 3 B | Bannerghatta on SH-87 to Besthamanahalli on SH-35 (including Anekal bypass, Grade separator across Chandapura road and ROB across railway line) via Jigani, Haragadde and Indalwadi (km 0+000 to km 22+980) in Bengaluru | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 119.79 | 128.79 | 29.76 | 14 | 59.22 | 90.14 | 30.75 | 194.11 | 12.879 | 64.395 | 51.516 |  | 128.79 | Financial bid placed before the board for approval
8 | 4A | Besthamanahalli (Anekal) on SH-35 to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield (km 0+000 to km 42+600) (excluding elevated corridor, Grade separator and ROB) in Bengaluru | Road | 39.28 | 312.08 | 168.16 | 219.51 | 19.72 | 22 | 96.15 | 144.49 | 49.44 | 312.08 | 21.951 | 109.755 | 87.804 |  | 219.51 | Financial bid placed before the board for approval
9 | 4 B | Construction of elevated corridor at Varthur village (1.300 km) in Bengaluru | Elevated Corridor | 1.3 km Elevated corridor | 286.62 | 175.64 | 157.56 | 1.78 | - | 108.31 | 132.93 | 45.38 | 286.62 | 15.756 | 78.78 | 63.024 |  | 157.56 | Retendered, Last Date of reciept: 05-02-2019
10 | 4 C | Construction of grade separators at Tally junction, Dommasandra junction, Varthur kodi junction and ROB at Kadugodi in Bangalore | Grade Separator & RoB | 3 Grade seperater 1 ROB | 133.94 | 48.8 | 64.33 | 3.8 | 9 | 41.27 | 62.27 | 21.4 | 133.94 | 6.433 | 32.165 | 25.732 |  | 64.33 | Financial bid placed before the board for approval
Total |  |  |  | 155.00 km | 2095 | 1335.6 | 1274.93 | 130.28 ( LA cost = Rs. 545 Cr) | 127.38 | 712.15 | 943.18 | 312.29 | 2095 | 142.341 | 689.265 | 712.674 |  | 1679.87

## Stretch wise details (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LIMITED
Development of Bengaluru surrounding Roads
Sl No | District | Division | Name of Work |  |  | Start | End | Total Length in km | Net Length in km | LA |  | LA Necessary | Encumberance free stretch | Length in km/Structure in No. | Total Estimated project cost | Contract Amount in Crore | Date of Agreement | Start Date (Site handed over on) | Due date of Completion | Contractor | Supervision Consultant | Remarks
1 | Bengaluru | Bengaluru | Package-1: | Development of Road from Hoskote Budigere Cross (NH-4) to Kempegowda International Airport road via Budigere-Singahalli and Mylanahalli (from Km 0+00 to 21+500) in Bangalore Urban/Rural District. | Stretch -1 | 0 | 20.11 | 20.11 | [5 empty] | 20.11 | 254 | 137.5189 | 2019-06-19 | 2019-07-01 | 2021-12-30 | M/s. S.R.C INFRA DEVELOPERS Pvt.Ltd. Bengaluru | M/s. Niketan Consultants, Bengaluru
|  |  | Total |  |  |  |  | 20.11
2 | Bengaluru | Bengaluru | Package-2A: | Development of Road from Nelamangala from NH-4 to Madhure on SH-74 via Chikkamadhure (from Km 0+00 to 15+250) in Bangalore. | Stretch -1 | 0 | 0.67 | 0.67 | 14.16 |  |  |  |  | 15.25 | 232.55 | 155.6938 | 2019-03-08 | 2019-04-29 | 2021-10-28 | M/s. STAR INFRATECH, Bengaluru | M/s. Infra Support Engineering Consultants Pvt. Ltd. Bengaluru
[5 empty] | Stretch -2 | 0.87 | 5.72 | 4.85
[5 empty] | Stretch -3 | 6.61 | 15.25 | 8.64
|  |  | Total |  |  |  |  | 14.16
3 | Bengaluru | Bengaluru | Package-2B: | Development of Road from Madhure on SH 74 to Devanahalli road (EMM VEE Solars on NH 7) via Rajanakunte and Thimmasandra (from Km 15+250 to 39+240). in Bangalore | Stretch -1 | 0 | 31.64 | 31.64 | 38.052 |  |  |  |  | 23.99 | 316.3 | 169.8099 | 2019-03-08 | 2019-06-20 | 2021-12-19 | M/s. BSR INFRATECH INDIA LIMITED, Bengaluru | M/s. Infra Support Engineering Consultants Pvt. Ltd. Bengaluru
[5 empty] | Stretch -2 | 32.24 | 36.54 | 4.3
[5 empty] | Stretch -3 | 37.15 | 39.262 | 2.112
|  |  | Total |  |  |  |  | 38.052
4 | Bengaluru | Bengaluru | Package-2C: | Construction of RUB at Basavanahalli Railway Crossing near Nelamangala Railway station (km 0+800) on SH 74 and ROB at Gollahalli Railway crossing (km 6+330) on SH 74 in Bangalore. | Stretch -1 | 0.67 | 0.87 | 0.2 | 1.09 |  |  |  |  | 1 RUB | 68.83 | 47.885 | 2019-03-08 | 2019-05-06 | 2021-11-05 | M/s. KMV PROJECTS LIMITED, Hyderabad | Tender Reinvited
[5 empty] | Stretch -2 | 5.72 | 6.61 | 0.89 | [5 empty] | 1 ROB
|  |  | Total |  |  |  |  | 1.09
5 | Bengaluru | Bengaluru | Package-2D: | Construction of ROB at Rajanakunte for crossing Railway line & SH 9 (Km 32+185) and ROB at Railway crossing at Narayanapura (Km 36+840) on MDR in Bangalore. | Stretch -1 | 31.64 | 32.24 | 0.6 | 1.21 |  |  |  |  | 2 ROB | 97.28 | 54.4803 | 2019-03-08 | 2019-04-04 | 2021-10-03 | M/s. P J B ENGINEERS PRIVATE LIMITED, Bengaluru
[5 empty] | Stretch -2 | 36.54 | 37.15 | 0.61
|  |  | Total |  |  |  |  | 1.21
6 | Bengaluru Ramanagaram | Bengaluru | Package-3A: | Development of road from Kanchugaranahalli to Jigani via Harohalli and Urgandoddi (km 0+000 to km 33+200) and section of road from BM road junction to Coca cola factory (km 0+000 to km 3+000) of Bidadi-Harohalli road in Bengaluru | Stretch -1 | 0 | 17.22 | 17.22 | 38.92 |  |  |  |  | 33.2 | 199.29 | 135.0843 | 2019-03-08 | 2019-06-21 | 2021-12-20 | M/s. K N R CONSTRUCTIONS LIMITED, Hyderabad | M/s. Apt Consulting Engineering Services, Bengaluru
[5 empty] | Stretch -2 | 23.1 | 33.2 | 10.1
[5 empty] | Additional Stretch | 0 | 11.6 | 11.6
[5 empty] | Descoped stretch | 17.22 | 23.1 | 5.88
|  |  | Total |  |  |  |  | 44.8
7 | Bengaluru | Bengaluru | Package-3B: | Development of road from Bannerghatta on SH-87 to Besthamanahalli on SH-35 (including Anekal bypass, Grade separator across Chandapura road and ROB across railway line) via Jigani, Haragadde and Indalwadi (km 0+000 to km 22+980) in Bengaluru | Stretch -1 | 0 | 6.22 | 6.22 | 17.04 |  |  |  |  | Road 22.98 km | 194.11 | 129.8922 | 2019-03-08 | 2019-05-06 | 2021-11-05 | M/s. KMV PROJECTS LIMITED, Hyderabad | M/s. COS Consultancy Services, Madurai
[5 empty] | Stretch -2 | 9.16 | 14.24 | 5.08
[5 empty] | Stretch -3 | 17.24 | 18.79 | 1.55
[5 empty] | Stretch -4 Bypass | 18.79 | 22.98 | 4.19 | [5 empty] | Grade seperater, ROB, Bypass
[5 empty] | Not included | 6.22 | 9.16 | 2.94
[5 empty] | Descoped stretch | 14.24 | 17.24 | 3
|  |  | Total |  |  |  |  | 22.98
8 | Bengaluru | Bengaluru | Package-4A: | Development of road from Besthamanahalli (Anekal) on SH-35 to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield length 39.280 (km 0+000 to km 42+600) (excluding elevated corridor, Grade separator and ROB) in Bengaluru | Stretch -1 | 0 | 6.491 | 6.491 | 34.421 | 3.6 | 6.491 | 2.891 | 3.6 | 39.28 | 312.08 | 182.2297 | 2019-03-08 | 2019-06-15 | 2021-12-14 | M/s. RNS INFRASTRUCTURE LIMITED, Bengaluru | M/s. Apt Consulting Engineering Services, Bengaluru
[5 empty] | Stretch -2 | 6.952 | 21.924 | 14.972 |  | 10.1 | 10.6 | 0.5 | 14.472
[5 empty] | Stretch -3 | 22.505 | 28.883 | 6.378 |  | 26.6 | 28.883 | 2.283 | 4.095
[5 empty] | Stretch -4 | 30.224 | 31.132 | 0.908 |  | 30.224 | 31.132 | 0.908 | 0 | [8 empty] | BBMP is doing work
[5 empty] | Stretch -5 | 33.32 | 35.83 | 2.51 |  | 33.32 | 34.51 | 1.19 | 1.32
[5 empty] | Stretch -6 | 36.498 | 37.44 | 0.942 |  | 36.498 | 37.458 | 0.96 | -0.018
[5 empty] | Stretch -7 | 40.44 | 42.66 | 2.22 |  | 39.458 | 42.66 | 3.202 | -0.982
[5 empty] | Not included | 31.682 | 33.32 | 1.638 | [13 empty] | To be surveyed for 6 lane | 37.44
[5 empty] | Descoped stretch | 37.44 | 40.44 | 3 | [13 empty] | BBMP whittapping working progress | 40.44
|  |  | Total |  |  |  |  | 39.059 |  |  |  | 11.934 | 22.487
9 | Bengaluru | Bengaluru | Package-4B: | Construction of Elevated Corridor at Varthur village (1.300 km) in Bengaluru | Stretch -1 | 28.883 | 29.08 | 0.197 | 1.341 | 28.883 | 29.08 | 0.197 | 0 | 1.30 Elevated Road | 286.62 | 163.18 | 2019-03-08 | 2019-05-20 | 2021-11-19 | M/s. NAGABHUSHANAM AND CO. Hyderabad | M/s. Mukesh & Associates , Salem
[5 empty] | Structure | 29.08 | 30.08 | 1 |  | 29.08 | 30.08 | 1 | 0
[5 empty] | Stretch -2 | 30.08 | 30.224 | 0.144 |  | 30.08 | 30.224 | 0.144 | 0
|  |  | Total |  |  |  |  | 1.341 |  |  |  | 1.341 | 0
10 | Bengaluru | Bengaluru | Package-4C: | Construction of Grade Separators at Tally Junction, Dommasandra Junction, Varthur Kodi Junction and ROB at Kadugodi in Bangalore | Stretch -1 | 6.491 | 6.641 | 0.15 | 0.461 | 6.491 | 6.641 | 0.15 | 0 | 3 Grade seperater 1 ROB | 133.94 | 65.1718 | 2019-03-08 | 2019-07-03 | 2022-01-04 | M/s. P J B ENGINEERS PRIVATE LIMITED, Bengaluru | M/s. C. V. Kand Consultants Pvt. Ltd. Bengaluru
[5 empty] | Structure-1 | 6.641 | 6.69 | 0.049 |  | 6.641 | 6.69 | 0.049 | 0
[5 empty] | Stretch -2 | 6.69 | 6.952 | 0.262 |  | 6.69 | 6.952 | 0.262 | 0
[5 empty] | Stretch -3 | 21.924 | 22.23 | 0.306 | 0.581 | 21.924 | 22.23 | 0.306 | 0
[5 empty] | Structure-2 | 22.23 | 22.29 | 0.06 |  | 22.23 | 22.29 | 0.06 | 0
[5 empty] | Stretch -4 | 22.29 | 22.505 | 0.215 |  | 22.29 | 22.505 | 0.215 | 0
[5 empty] | Stretch -5 | 31.132 | 31.34 | 0.208 | 0.55 | 31.132 | 31.34 | 0.208 | 0
[5 empty] | Structure-3 | 31.34 | 31.467 | 0.127 |  | 31.34 | 31.467 | 0.127 | 0
[5 empty] | Stretch -6 | 31.467 | 31.682 | 0.215 |  | 31.467 | 31.682 | 0.215 | 0
[5 empty] | Stretch -7 | 35.83 | 36.014 | 0.184 | 0.668 | 35.83 | 36.014 | 0.184 | 0
[5 empty] | Structure-4 | 36.014 | 36.112 | 0.098 |  | 36.014 | 36.112 | 0.098 | 0
[5 empty] | Stretch -8 | 36.112 | 36.498 | 0.386 |  | 36.112 | 36.498 | 0.386 | 0
|  |  | Total |  |  |  |  | 2.26 | 2.26 |  |  | 2.26 | 0

## status of the roads (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LTD.
DETAILS OF ROADS AROUND BENGALURU PROPOSED FOR DEVELOPMENT (IN 10 PACKAGES )
Total Length of Road 155 Km, Project cost Rs.2095 Crore
(Amount in Crore)
Sl.No | Package No | Name of the work | Nature of work | Length (In km) | Total project cost (In crore) | Contract amount exckluding GST | Tentative LA cost | Micelleanous and ultility shifting | Date of Site Hand over | Land Acquisition | Tree cutting as per DFR | Tree cutting |  | Water supply pipe line shifting | Electrical Line shifting | Tank Bund Details​ | Tele poles | Traffic poles | Transformers | UD units | Physical status as on 02-12-2019 | Physical status | Agency | Tender Premium | Expected GST (12% of Quoted) | Total | Mobilisation advance
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 17 | 18 | 19 | 20 | 21 |  | 16 |  |  | 11 | 12=10+11 | 13
1 | 1 | Hoskote Budigere cross (NH-4) to Kempegowda international airport road via Budigere- Singahalli and Mylanahalli | Road | 20.11 | 254 | 137.52 | 53.1 | 54.5 | 2019-07-01 | *KR Puram 10 villages JMC completed (Ch. 3+700 to 8+300), *Devanahalli 3 villages JMC completed (Ch. 8+300 to 13+000) * Yelahanka 5 villages JMC sheduled from 26/11/2019 (Ch. 13+000 to 20+100) | 725 Tree cutting proposals to be sent to concerned DFO | KR Puram RFO Devanahalli RFO Yelahanka RFO | * (From Ch. 0+000 to 8+300) Revised Tree Enumeration is in progress for KR Puram Range. * Tree cutting Permission obtained for 220 No's (Ch. 8+300 to 13+300) Devanahalli, charges remitted for RFO, work order issued by DCF (R) by Auction to external agency, work to be started. * (From Ch.13+300 to 20+110) Revised Tree Enumeration submitted to Yelahanka RFO | * water supply estimate to be submitted for EE, RWS Hoskote &Devanahalli Rs.150.00 lakh, | * Electrical estimate: KR Puram 7.2 Cr. (Ch. 0+000 to 8+600) at CE BESCOM * Devanahalli subdivison 3.27 Crore (Ch. 8+600 to 13+000) at SE BESCOM * Yelahanka 24.13 Crore (Ch. 13+000 to 20+100 at CE BESCOM submitted to Division and is awaited. | Nil | [5 empty] | * SIA completed. * Fixing of Revised ROW and Boundary stone for additional 1.0 m width for utility corridor is completed. * Plan and Profile, along with Structures (except 1-Minor bridge & 0.6 km KIA land & 0.37 km substation location) for entire stretch submitted to PMC and Proof checked drawings is submitted. * Survey No. 31 near mandur is identified as a Govt. land for Toll Plaza. * Site office & & lab executed. * widening of 6 culverts is in Progress, steel fabrication started * 13+700 to 14+100(GAIL gas station & singanahalli) Subgrade top level on RHS completed. | RAJAGOPAL MUTTINENI (S.R.CONSTRUCTIONS) | 2.637% | 6.54 | 61.04 | 3.052
2 | 2A | Nelamangala to Madhure on SH 74 via Chikkamadhure from 0+00 to 15+250 | Road | 15.25 | 232.55 | 155.69 | 24.05 | 51.9 | 2019-04-29 | * out of 12, 11 villages (except Golahalli) JMC completed, JMC sketche preparation with extents is under progress. Building valuation is in progress. | 3045 Tree cutting proposals to be sent to concerned DFO. | Nelamangala RFO ​ Doddaballapur RFO Doddaballapura ACF Bengaluru Rural Dist DCF | CH:0+000to CH:8+810 =484 Nos CH:8+810 to CH:15+250 = 645 Nos Total : 1129 No.s Intimation letter from DCF rural received & amount is remitted on 16/08/2019, *DCF (R) had forwarded the proposal to the expert Committee on 19-11-2019, * it concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and * action to be taken for providing land min. width of 1.5 m on either side of ROW for relocating Native Species trees. work order for Tree cutting to be issued from the DCF (R) to the Auction agency or Representative of KRDCL | * Estimate received from AEE, RWS, Nelamangala, of Rs.30.00 lakh, (Ch 0+00 to 8+50) * Estimate received from AEE, RWS, Doddaballapur, of Rs.13.00 lakh, (Ch 10+530 to 11+090) & (Ch.12+610 to 13+830) Above estimates have been sent for Technical Scrutiny to EE, RWS, Blore (R) on 08-11-2019 | * CH:0+000to CH:0+65 Nelamangal O&M 1: 4.42 Cr (supervision charges to be deposited from KRDCL) * CH:0+650 to CH: 8+81 Nelamangal O&M 2: 11.28 Cr (supervision charges to be deposited from KRDCL) * CH:8+810 to CH:15+250 Doddaballapura : 3.20 Cr (supervision charges deposited) Work order to be issued from BESCOM Doddaballapura. Total : 18.9 Cr | Widening of Tank bund on the D/S of Madhurai tank for a Length - 1340 mtr with 4L+PS/ES CH:13+760 to CH:15+100 | letter addressed to all agencies to shift their lines out of our ROW |  |  |  | * SIA completed - Final notification to be issued. * Fixing of ROW completed & Boundary stone fixing is in progress. * Site office & lab executed. * Construction of Retaining wall and Culverts - Earth work Excavation is in Progress | * SIA completed - Final notification to be issued. * Fixing of ROW completed & Boundary stone fixing is in progress. * Site office & lab executed. * Construction of Retaining wall and Culverts - Earth work Excavation is in Progress | STAR INFRATECH | 115.8% | 6.228 | 58.128 | 2.9064
3 | 2 B | Madhure on SH 74 to Devanahalli road (MV Solars on NH7) via Rajanukunte and Thimmasandra (Ch15+250 to 39+240) | Road | 23.99 | 316.3 | 169.81 | 81.05 | 61 | 2019-06-20 | * Out of 16, 15 villages (except Rajankunte) JMC completed. JMC sketche preparation with extents is under progress |  | Doddaballapur RFO Doddaballapura ACF Bengaluru Rural Dist DCF Malleshwaram RFO ​ Yellanhanka Div 1 RFO ​ Yellanhanka Div 2 RFO Bengaluru North ACF Bengaluru Urban Dist DCF | Ch. 15.25-19.33 =176 No's (Intimation letter received) paid dated 16/08/2019 CH:19+330 to CH:30+240 = 946 Nos CH:30+240 to CH:33+720 = 396 Nos CH:33+720 to CH:39+260= 407 Nos Total : 1925 No.s *DCF (R) &(U) had presented the proposal to the expert Committee on 19-11-2019, * it concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and * action to be taken for providing land min. width of 1.5 m on either side of ROW for relocating Native Species trees. work order for Tree cutting to be issued from the DCF (R) & (U)to the Auction agency or Representative of KRDCL | * Estimate received from AEE, RWS, Doddaballapur, of Rs.15.60 lakh, (Ch 15+250 to 19+00) & * 3 Estimates received from AEE, RWS, Bengaluru (U) North Ta, of Rs.135.41 lakh, (Ch 19+00 to 39+24) Above estimates have been sent for Technical Scrutiny to EE, RWS, Blore (R) &(U) on 08-11-2019 & 20-11-2019 | Electrical estimates is submitted to EE, BESCOM Yelahanka Division and Approval is awaited | Widening of Tank bund on the D/S of tank of Length - 700 mtr with 4L+PS/ES CH:23+400 to CH:24+100 | letter addressed to all agencies to shift their lines out of our ROW |  |  |  | * SIA completed - Final notification to be issued. * Fixing of ROW completed & Boundary stone fixing is in progress. * Site office & lab executed. * Construction of Culverts at 8 location- Earth work Excavation, Concreting to culverts is in progress | * SIA completed - Final notification to be issued. * Fixing of ROW completed & Boundary stone fixing is in progress. * Site office & lab executed. * Construction of Culverts at 8 location- Earth work Excavation,PCC is in progress | SRINIVASA RAO BALUSU (BSR INFRATECH INDIA LIMITED) | -24.74% | 7.32 | 68.32 | 3.416
4 | 2 C | Construction of RUB at Basavanahalli Railway crossing near Nelamangala railway station (km 0+800) on SH 74 AND | RUB | 1 RUB | 68.83 | 47.89 | 6.08 | 12.75 | 2019-05-06 | * JMC completed, JMC sketche preparation with extents is under progress |  |  | RUB stretch is included in the proposal of Pkg 2A | RUB stretch is included in the proposal of Pkg 2A | RUB stretch is included in the proposal of Pkg 2A | Nil |  |  |  |  | * SIA completed • RUB GAD submitted on 05-08-2019 to Railway authority. Queries were complied on17-10-2019 Approval is awaited from Railway Authority | * SIA completed • RUB GAD submitted on 05-08-2019 to Railway authority. Queries were complied on17-10-2019 Approval is awaited from Railway Authority
|  | Construction of ROB at Gollahalli railway crossing (km 6+300) on SH 74 | ROB | 1 ROB |  |  |  |  | 2019-05-06 | * JMC is scheduled for Golahalli village Stretch on 26-11-2019 (GAD finalised on 20-11-2019) |  |  | ROB stretch is included in the proposal of Pkg 2A | ROB stretch is included in the proposal of Pkg 2A | ROB stretch is included in the proposal of Pkg 2A | Nil |  |  |  |  | * SIA completed • • ROB GAD submitted on 21-11-2019 to Railway authority. Approval is awaited from Railway Authority | * SIA completed • • ROB GAD submitted on 21-11-2019 to Railway authority. Approval is awaited from Railway Authority | KMV PRASAD RAO (KMV PROJECTS LIMITED) | 10.5% | 1.53 | 14.28 | 0.714
5 | 2 D | Construction of ROB at Rajanakunte for crossing railway line & SH 9 (km 32+185) AND | ROB | 1 ROB | 97.28 | 54.48 | 9.83 | 17.45 | 2019-04-04 | * New alignment to be freezed, preliminary notification to be issued, * SIA to be initiaed, after ROB GAD is finalized. |  |  | This stretch is included in the proposal of Pkg 2B | This stretch is included in the proposal of Pkg 2B | This stretch is included in the proposal of Pkg 2B | Nil | New alignment to be freezed, accordingly estimate will be initiated |  |  | New alignment to be freezed, accordingly estimate will be initiated |  | • GAD to be submitted to Railway authority but MLA has proposed an additional two lane ROB along with the existing. Revised GAD to be submitted by the Agency along with LAP and cost Estimate
|  | Construction of ROB at railway crossing at Narayanapura (km 36+840) on MDR | ROB | 1 ROB |  |  |  |  | 2019-04-04 | * JMC completed, Sketches are awaited from ADLR Yelahanka |  |  | This stretch is included in the proposal of Pkg 2B | This stretch is included in the proposal of Pkg 2B | This stretch is included in the proposal of Pkg 2B | Nil | Nil | Nil |  | Nil |  | • GAD submitted to Railway authority along with the compliance to observations raised * SIA completed - Final notification to be issued. | P J B ENGINEERS PRIVATE LIMITED | 77.52% | 2.094 | 19.544 | 0.9772
6 | 3A | Bidadi to Kanchagaranahalli (km 0+000 to km 7+000) and Kanchugaranahalli to Jigani via Harohalli and Urgandoddi (km 0+000 to km 33+200) | Road | 33.2 | 199.29 | 135.08 | 37.22 | 40.67 | 2019-06-20 | *Harohalli By pass revised alignment is approved by Technical Committee accordingly LA plan revised and submitted to Government for approval for preliminary notification | 392 Tree cutting proposals to be sent to concerned DFO. | Kanakapura RFO Anekal RFO | Ch. 0.00 to 17.200 Km total no of trees 652 ACF (Ramnagagr ACF) * Tree cutting permission recieved , charges to be remitted to Forest Dept From contractor to issue the Work order from DCF (R) *Ch. 23.00 to 33.20 km No of trees 184. Tree cutting permission awaited, the proposal is to be placed before the committee. | water supply line identified, estimate under preparation by RWS Dept. | AEE, Harohalli sub division (intimation letter recieved & amount paid of Rs. 17,93,600 + 62,587 ) work order issued from BESCOM dated:08-11-2019 and AEE, Jigani sub division (intimation letter recieved & amount paid of Rs. 17,93,600 + 19, 258) work order issued from BESCOM dated 08-11-2019 Suplimentary Agreement to be executed, Electrical work will be started | Nil |  |  |  |  | *Harohalli By pass revised alignment is approved by Technical Committee accordingly LA plan revised and submitted to Government for approval, Accordingly Notice will be issued to the land owner. *Krishnanadoddi By-pass alignment fixed. SIA to be initiated * Except By-pass fixing of ROW is completed. * The proposal for 4Lane from Kanchagaranahalli to Harohalli (0.00 to 4.50 km) as per the instructions of MD, KRDCL during site visit. topo survey completed, LA is in progress, *Supervision charges paid, MOU signed from KRDCL for self execution. | *Harohalli By pass revised alignment is approved by Technical Committee accordingly LA plan revised and submitted to Government for approval, Accordingly Notice will be issued to the land owner. *Krishnanadoddi By-pass alignment fixed. SIA to be initiated * Except By-pass fixing of ROW is completed. * Electrical estimate recieved from BESCOM, supervision charges paid. work order issued dated:08-11-2019 from BESCOM. MOU between BESCOM & KRDCL to be excuted. Work will be started shortly. * The proposal for 4Lane from Kanchagaranahalli to Harohalli (0.00 to 4.50 km) as per the instructions of MD, KRDCL during site visit. topo survey completed, LA is in progress, * Public are objecting to take up the drain work at the edge of the Carrageway instead they are asking to execute at boundary of the project stretch, accordingly action is initiated. * proposal submitted for approval of quarry to DC Ramnagara | TIRUPATHI REDDY DEVARAPALLI (K N R CONSTRUCTIONS LIMITED) | 9.269% | 4.8804 | 45.5504 | 2.2775
7 | 3 B | Bannerghatta on SH-87 to Anekal (Besthamanahalli) on SH-35 via Jigani, Haragadde and Indalwadi (Ch 0+000 to 22+980) | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 129.89 | 34.19 | 40.13 | 2019-05-06 | Anekal By-pass alignment passes through existing Karpura kere water body, hence it attracts environamental issues. MD instructed during site visit dated 07-11-2019 to realign the Bypass with alternative proposals wthin a week. | 104 Tree cutting proposals to be sent to concerned DFO. | Anekal RFO, | Total: 520 No's LHS - Ch.0+000 toCh.18+180 =319 No's RHS - Ch. 0+000 toCh. 17+000 = 201 No's * Tree cutting awaited, letter sent dated: 01/04/2019 & Proposal will be placed before committee on 19-11-2019 for decission | water supply line identified, estimate under preparation by RWS Dept. | AEE, Jigni sub division Ch. 0.000 to 13.600 (intimation letter recieved & amount paid of Rs. 17,93,600 SC ) dated : 12-10-2019 and MOU executed between BESCOM & KRDCL, dated: 07-11-2019, work order awaited from BESCOM. AEE, Anekal sub division Ch. 13.600 to Ch. 18.250 (intimation letter recieved & amount paid of Rs. 17,93,600 SC ) dated : 12-10-2019 and MOU executed between BESCOM & KRDCL, dated: 07-11-2019, work order awaited from BESCOM. (Anekal bypass 18.25 to 22.972 pending) | I. Anekal Doddakare bund length = 1.400 km,Ch. 16+900 to Ch. 18+300 LA required: 12m for widening along LHS of the Lake II. Karapura Kare inside the lake for a length of 0.500 km, Ch.21+450 to Ch.21+950 – LA required: 24m |  |  |  |  | * Except By-pass fixing of ROW is completed, * Proposed Anekal By-pass alignment is placed before the Technical Committee on 07-12-2019 for approval * | * Except By-pass fixing of ROW is completed * Site office, Laboratory & batch mix plant, construction work is in progress. | KMV PRASAD RAO (KMV PROJECTS LIMITED) | 17.37% | 4.8156 | 44.9456 | 2.2473
8 | 4A | Anekal (Besthamanahalli) on SH-35 to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield (Ch 0+000 to 42+600) (excluding elevated corridor, Grade separator and ROB) | Road | 39.28 | 312.08 | 182.23 | 106.93 | 30.2 | 2019-06-15 | * CRP meeting was conducted on 18/07/2019 * JMC & SIA shall be initiated by the first week of December. | 1658 Tree cutting proposals to be sent to concerned DFO. | Anekal RFO, Mahadevapura RFO | Ch.0+000 to Ch.25+000 proposal to be forwarded from RFO to ACF. Ch.25+000 to Ch.42+660 Tree cutting permission awaited, RFO apraised on 24/10/2019 * Reminder letter is also issued to DCF to issue the permission. | water supply line identified upto 28 km, estimate under preparation by RWS Dept and remaining to be interacted with BWSSB & MI. | *Anekal subdivision 2.67 Crore (Ch. 0+000 to 1+600),submitted to EE *Attibele (Mayasandra) subdivision10.21 Cr (Ch.1+600 to 6+500) submitted to EE *Attibele subdivision 11.17 Cr (Ch.6+500 to 10+000) submitted to EE *Attibele (Sarjapura) subdivision 43.01 Cr (Ch.10+000 to 22+000) to be submitted from AEE *Attibele (Dommasandra) subdivision 9.67 Cr (Ch.22+000 to 26+000) to be submitted from AEE *Mahadevapura subdivision---- Cr (Ch.26+000 to 36+000) estimate under preparation *Avalahalli subdivision 6.83 Cr (Ch.36+000 to43+000) submitted to EE | Proposed for widening of Tank bund I.Mayasandra tank bund length = 100 m, Ch. 2+800 to Ch. 2+900 II. Bidarguppa tank bund length =650 mt Ch. 10+050 to Ch. 10+700 III. Varthur tank bund length =513 mt Ch. 30+620 to Ch. 31+133 |  |  |  |  | Total length of Road - 4: 42.66 Km Deduction : - Pkg 4B : 1.92 km - Pkg 4C : 2.26 km - Descoped stretch : 3.00 km - Not included stretch : 1.64 km The net road length =33.84 km *Out of 33.84 km, upto 19.40 km fixing of ROW & Boundary stone completed and remaining is in progress. * Horizontal Alignment Approved by PMC * OGL Survey is in Progress (completed from Ch. 0+000 to 19+400 & Ch. 41+700 to 42+600km) * Site office & plant is at Jigani, which is about 20km away from the project road. | Total length of Road - 4: 42.66 Km Deduction : - Pkg 4B : 1.92 km - Pkg 4C : 2.26 km - Descoped stretch : 3.00 km - Not included stretch : 1.64 km The net road length =33.84 km *Out of 33.84 km, upto 18.94 km fixing of ROW & Boundary stone completed and remaining is in progress. * Alignment Report Submitted by Agency on 26-10-2019, Proof checking is in progress. * OGL Survey is in Progress (completed upto 12.14 km) * Site office & plant is at Jigani, which is about 20km away from the project road. | P J B ENGINEERS PRIVATE LIMITED | -74.78% | 3.624 | 33.824 | 1.6912
9 | 4 B | Construction of Elevated Corridor at Varthur village (1.300 km) | Elevated Corridor | 1.3 km Elevated corridor | 286.62 | 163.18 | 123.76 | 0 | 2019-05-20 | * Proposal sent to Govt. except village limit (SIA to be initiated immediately) * LA plan for 100 ft width is submitted to LAQ section. * Collection of Details of Structures for proposed 100 ft width is in progress, will be submitted before 05/11/2019 |  | BBMP RFO | Ch.28+700 to Ch. 30+620 = 49 No's * Tree cutting permission shall be done with Pkg 4A Agency. | Relocation of BWSSB Water Supply lines has to coordinated with Pkg 4A Agency. | Ch.28+700 to Ch. 30+620 = 109 No's * Electrical Estimate to be prepared based on the fixing of ROW (100ft/ 60ft) | existing servicde road over the tankbund is avoided and realignment | nil | nil | Ch.28+700 to Ch. 30+620 = 8 No's | Ch.28+600 to Ch. 30+300 =2 No's |  | * Public have not allowed to do the survey work & on request of public representative they have agreed in condition, if 100 ft width flyover is to be executed. * GAD for 100 ft width is submitted and the same is verified and proof checked by PMC with observations, Same to be complied along with cost estimate by Agency. | Nagabhushan Constrctions Pvt. Ltd., Hyderabad | 10.5% | 0 | 0 | 0
10 | 4 C | Construction of grade separators at Tally junction, | GS | GS | 133.94 | 65.17 | 68.79 | 10.35 |  | After finalization of GAD LA plan will be submitted |  | Anekal RFO | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A | [5 empty] | *Revised GAD with proposal of improving S-curve is awaited from EPC contractor *Geotechnical investgation completed, Submission of report awaited | *GAD to be submitted by the agency and committed to submit on 26-11-2019,
|  | Construction of grade separators at Dommasandra junction, | GS | GS | [5 empty] | After finalization of GAD LA plan will be submitted |  | Anekal RFO | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A | [5 empty] | *Proposal submitted by EPC contractor, Marking completed, LA statement & ROW statement prepared, For finalization of Proposal & minimize LA inspection from jai Prasad sir is awaited *Geotechnical investgation completed, Submission of report awaited | * GAD submitted with 2 wings 1 towards Airport & another towards ORR, but DFR has only 1 wing towards Airport, As per the discussion, Site visit, Technical Committee chairmen instructed to go for elevated road from Sarjapur to ORR and Sub way to Airport accordingly Modified GAD will be submitted on 26-11-2019 along with cost Estimate
|  | Construction of grade separators at Varthur kodi junction | GS | GS | [5 empty] | After finalization of GAD LA plan will be submitted |  | Mahadevapura RFO | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A | [5 empty] | *Revised GAD with proposal is under discussion, Center line &pier location with Rotary proposal marked at site *Geotechnical investgation completed, Submission of report awaited | *GAD to be submitted by the agency and committed to submit on 26-11-2019
|  | Construction of ROB at Kadugodi | RoB | RoB | [5 empty] | After finalization of GAD LA plan will be submitted |  | Mahadevapura RFO | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A | This stretch is included in the proposal of Pkg 4A |  |  |  | RHS - 1 No LHS - 4 No's Ch.63+900 to Ch. 70+400 RHS - 6 No's LHS - 6 No's Ch.21+920 to Ch. 22+515 (Battery limit) |  | *Revised proposal need to be submitted from EPC contractor | * GAD submitted to be submitted As per the discussion, Site visit, and instructions made by the higher authority and will be submitted on 26-11-2019 along with cost Estimate | NAVEEN RAMA SHETTY (RNS INFRASTRUCTURE LIMITED) | -84.95% | 1.242 | 11.592 | 0.5796
| Total for 10 Packages: |  |  |  | 2095 | 1240.94 | 545 | 318.95 | [16 empty] | 38.274 | 357.224 | 17.8612

## Forest Dept (2)
DEVELOPMENT OF ROADS AROUND BENGALURU (10 PACKAGES)
Forest Department Issues | [16 empty] | Date: 19-01-2020
Sl.No | Pkg No | Name of the work | Nature of work | Length (In km) | Total project cost (In crore) | Contract amount exckluding GST | Tentative LA cost | Micelleanous and ultility shifting | Date of Site Hand over | Tree cutting as per DFR | Chainage | Range | No. of trees |  |  | Status | Action to be taken
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 8 | 12 | 4 | 5 | 6 | Tobecut | TobeTransplanted | 7 | 8
1 | 1 | Hoskote Budigere cross (NH-4) to KIAL via Budigere | Road | 20.11 | 254 | 137.52 | 53.1 | 54.5 | 2019-07-01 | 725 Tree cutting proposals to be sent to concerned DFO | Ch. 0+000 to 8+300 | RFO - KR Puram range, ACF & DCF -Bangalore (U) | T =1505 S = 100 Trp = 70 C =1335 |  |  | * DCF (U) had presented the proposal to the expert Committee on 18-12-2019, * It concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and action to be taken for relocating Native Species trees and also to increase the no of trees to be transplanted and to be placed before the next committee on or before 1st week of January. * Accordingly Public consultation meeting is held on 24-12-2019 & found positive response from public for tree cutting * Tree expert committee members visited the site dated :28-12-2019, members proposed to place before the next committee. | * Proposal to be placed before the next expert committee is scheduled on 21-01-2020 * After approval, to give permision to the KRDCL Contractor to fell the tree as per the Govt Order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price.
[11 empty] | Ch. 8+300 to 13+300 | RFO - Devanahalli, ACF & DCF -Bangalore (R) | T =9 C = 9 |  |  | * Tree cutting Permission given for 9 trees, work order issued to Kaleel sab (external agency). Tree cutting completed. | Tree cutting completed
[11 empty] | Ch.13+300 to 20+110 | RFO -Yelahanka, ACF & DCF - Bangalore (U) | T =423 Trp = 9 C =414 |  |  | * DCF (U) had presented the proposal to the expert Committee on 18-12-2019. * It concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and action to be taken for relocating Native Species trees and also to increase the no of trees to be transplanted and to be placed before the next committee on or before 1st week of January. * Accordingly Public consultation meeting is held on 17-01-2020 & identified no of transplantation trees | * Proposal to be placed before the next expert committee is scheduled on 21-01-2020 * After approval, to give permision to the KRDCL Contractor to fell the tree as per the Govt Order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price
2 | 2A | Nelamangala to Madhure on SH 74 via Chikkamadhure |  | 15.25 | 232.55 | 155.69 |  |  | 2019-04-29 |  | Ch.0+000 to 8+810 | ACF -Doddaballapura DCF - Bengaluru Rural Dist | T= 484 S = 30 Trp = 125 C = 329 |  |  | *DCF (R) had forwarded the proposal to the expert Committee on 19-11-2019 & 18-12-2019, * It concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and same to be place before the next expert committee shall be scheduled in 1st week of January for approval. * Public consultation meeting is scheduled on 30-12-2019 | * Proposal to be placed before the next expert committee is scheduled on 21-01-2020 * To give direction to issue the work order from the DCF (R) to KRDCL or its Representative for felling of trees as per the govt order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price.
[11 empty] | Ch.8+810 to 15+250 |  | T= 645 S = 5 Trp = 100 C =540
3 | 2 B | Madhure on SH 74 to Devanahalli road via Rajanukunte |  | 23.99 | 316.3 | 169.81 |  |  | 2019-06-20 |  | Ch.15+250 to 19+330 | ACF -Doddaballapura DCF -Bengaluru Rural Dist | 176 |  |  | Intimation letter received & amount paid from KRDCL *DCF (R) had presented the proposal to the expert Committee on 19-11-2019, * It concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and same to be place before the next expert committee shall be scheduled in 1st week of January for approval. * Public consultation meeting is scheduled on 30-12-2019 | * Proposal to be placed before the next expert committee is scheduled on 21-01-2020 * To give direction to issue the work order from the DCF (R) to KRDCL or its Representative for felling of trees as per the govt order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price.
|  |  |  | 23.99 | 316.3 | 169.81 |  | 61 | 2019-06-20 |  | Ch.19+330 to 39+260 | RFO - Yelahanka & Bengaluru North ACF - Bengaluru North DCF - Bengaluru Urban Dist | T =1782 S =43 Trp = 325 C =1414 |  |  | * DCF (U) had presented the proposal to the expert Committee on 18-12-2019, * It concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and action to be taken for relocating Native Species trees and also to increase the no of trees to be transplanted and to be placed before the next committee on or before 1st week of January. * Accordingly Public consultation meeting is scheduled on 27-12-2019 | * Proposal to be placed before the next expert committee is scheduled on 21-01-2020 * After approval, to give permision to the KRDCL Contractor to fell the tree as per the Govt Order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price..
3 | 2B | Madhure on SH 74 to Devanahalli road via Rajanukunte | Road |  |  |  | 81.05 |  |  |  | Ch.18+000 to 18+200 & Ch.19+000 to 19+200 | ACF -Doddaballapura DCF - Bengaluru Rural Dist | 250 |  |  | Survey no. 37, Junnasandra village, Doddaballapura Taluk,extent 5 acres, required for realignmnet of sharp curves to improve the geomertics of curve as per IRC standards | As per the IRC standards for 4 Lane Road it is required to improve the sharp curve with Minimum Radius for the design speed which passes through the forest land considering the Technical aspects, it is requested to provide the Forest Land of about 4.5 acre in respect of safety of road user. Accordingly online application will be submitted within a week.
4 | 3A | Bidadi to Jigani via Harohalli and Urgandoddi |  | 33.2 | 199.29 | 135.08 |  | 40.67 | 2019-06-20 |  | Ch. 0+000 to 4+500, 7+00 to 21+00 and 22+00 to 23+00 | ACF & DCF -Ramanagara | 652 |  |  | *Afforestaion and development charges of Rs. 78,06,000/- remitted to DFO, Ramanagar from KRDCL. * Upset price including satutary Taxes and Charges has been paid of Rs. 10,17,039/- by the agency. | * Work order to be issued from the DCF, Ramnagara to KRDCL at said amount for felling of trees as per the govt order No.FEE/168/FDP/2017 Dated:06-12-2018. * It is instructed to Agency to proceed with the felling of trees by taking consent with the Forest Department. * Tree cutting strated from KRDCL agency
|  |  | Road |  |  |  | 37.22 |  |  | 392 Tree cutting proposals to be sent to concerned DFO. | Ch.23+000 to 33+200 | ACF & DCF -Bengaluru urban | 184 |  |  | * DCF (U) has been placed the proposal to the expert Committee on 19-11-2019 & 18-12-2019, * It concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and action to be taken for relocating Native Species trees and also to increase the no of trees to be transplanted and to be placed before the next committee on or before 1st week of January. * Accordingly Public consultation meeting is held on 24-12-2019 & found positive response from public for tree cutting | * Proposal to be placed before the next expert committee is scheduled on 21-01-2020 After approval, to give permision to the KRDCL Contractor to fell the tree as per the Govt Order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price.
5 | 3 B | Bannerghatta on SH-87 to Anekal (SH-35) via Jigani, | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 129.89 | 34.19 | 40.13 | 2019-05-06 | 104 Tree cutting proposals to be sent to concerned DFO. | Ch.0+000 to 18+180 | ACF & DCF Bengaluru urban | 520 |  |  | * DCF (U) has been placed the proposal to the expert Committee on 19-11-2019 & 18-12-2019, * It concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and action to be taken for relocating Native Species trees and also to increase the no of trees to be transplanted and to be placed before the next committee on or before 1st week of January. * Accordingly Public consultation meeting is held on 24-12-2019 & found positive response from public for tree cutting | * Proposal to be forwarded to approval to place before the next expert committee shall be scheduled in 1st week of January for approval. After approval, to give permision to the KRDCL Contractor to fell the tree as per the Govt Order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price.
6 | 4A | Anekal to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield |  | 39.28 | 312.08 | 182.23 |  | 30.2 | 2019-06-15 |  | Ch.0+000 to 25+000 | ACF - Bengaluru urban | T = 1406 Trp = 63 c = 1343 |  |  | Revised enumaration of trees is in progress, revised proposal to be forwarded from RFO to ACF. | * Proposal to be placed before the next expert committee is scheduled on 21-01-2020 After approval, to give permision to the KRDCL Contractor to fell the tree as per the Govt order No.FEE/168/FDP/2017 Dated:06-12-2018 at upset price.
[11 empty] | Ch.25+000 to 26+500 | ACF - Bengaluru urban | T =1782 S =43 Trp = 325 C =1414 |  |  | Enumaration of trees is in progress, proposal to be forwarded from RFO to ACF.
[11 empty] | Ch.26+500 to 36+500 | BBMP forest ACF- Bengaluru urban | 883 |  |  | Revised enumaration of trees is in progress, revised proposal to be forwarded from RFO to ACF.
|  |  | Road |  |  |  | 106.93 |  |  | 1658 Tree cutting proposals to be sent to concerned DFO. | Ch.36+500 to 42+660 | ACF - Bengaluru urban | need to find this out |  |  | Revised enumaration of trees is in progress, revised proposal to be forwarded from RFO to ACF.
T = Total No of Trees, S = No of trees may be saved, Trp = No of trees proposed for Transplantation, C = No of trees proposed for Cutting

## electrical (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LTD.
DEVELOPMENT OF ROADS AROUND BENGALURU | [15 empty] | Date: 06-12-2019
Total Length of Road 155 Km, Project cost Rs.2095 Crore
BESCOM Department
Sl.No | Pkg No | Name of work | Nature of work | Length (In km) | Total project cost (In crore) | Contract amount exckluding GST | Tentative LA cost | Micelleanous and ultility shifting cost in Cr. | Date of Site Hand over | Tree cutting as per DFR | Chainage | Division | Amount | Estimate cost in Cr. | Status | Action to be taken
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 4 | 5 |  | 6 | 7 | 8
1 | 1 | Hoskote Budigere cross (NH-4) to KIAL via Budigere | Road | 20.11 | 254 | 137.52 | 53.1 | 54.5 | 2019-07-01 | 725 Tree cutting proposals to be sent to concerned DFO | Ch. 0+000 to 8+600 | Avalahalli sub division + O&M |  | 7.13 | intimation letter recieved on 12-12-2019 | Approval awaited from BESCOM for shifting of Electrical lines. After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate.
[11 empty] | Ch. 8+600 to 13+000 | Sadahalli cross O&M, Devanahalli subdivision |  | 3.24 | intimation letter recieved on 12-12-2020
[11 empty] | Ch. 13+000 to 20+100 | Sadahalli cross O&M , Vidyanagara subdivision |  | 25.15 | intimation letter recieved on 12-12-2021
2 | 2A | Nelamangala to Madhure on SH 74 via Chikkamadhure | Road | 15.25 | 232.55 | 155.69 | 24.05 | 51.9 | 2019-04-29 | 3045 Tree cutting proposals to be sent to concerned DFO. | Ch:0+000 to 0+650 | Nelamangal O&M 1 |  | 4.42 | supervision charges deposited from KRDCL to BESCOM dated: 27-11-2019. MOU to be signed between KRDCL for self execution | Payment made for supervision charges. After signing of Undertaking for self execution & Work order to be issued from BESCOM
[11 empty] | Ch:0+650 to 8+810 | Nelamangal O&M 2 |  | 11.28 | supervision charges deposited from KRDCL to BESCOM dated: 27-11-2019. MOU to be signed between KRDCL for self execution
[11 empty] | Ch:8+810 to 15+250 | Doddaballapura |  | 3.2 | supervision charges deposited, Work order to be issued from BESCOM.
3 | 2 B | Madhure on SH 74 to Devanahalli road via Rajanukunte | Road | 23.99 | 316.3 | 169.81 | 81.05 | 61 | 2019-06-20 |  | Ch15+250 to 19+300 | Doddaballapura |  | - | Electrical estimates is submitted to CE, BESCOM and Approval is awaited | Approval awited from BESCOM After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate. MOU to be signed between KRDCL & BESCOM for self execution
[11 empty] | Ch19+300 to 35+00 | Yelahanka |  | - | Electrical estimates is submitted to CE, BESCOM and Approval is awaited | Approval awited from BESCOM After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate. MOU to be signed between KRDCL & BESCOM for self execution
[11 empty] | Ch39+00 to 39+240 | Vidyanagara |  | 28.57 | Electrical estimates is submitted to CE, BESCOM and Approval is awaited | Approval awited from BESCOM After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate. MOU to be signed between KRDCL & BESCOM for self execution
4 | 3A | Bidadi to Jigani via Harohalli and Urgandoddi | Road | 33.2 | 199.29 | 135.08 | 37.22 | 40.67 | 2019-06-20 | 392 Tree cutting proposals to be sent to concerned DFO. | Ch:0+000 to 23+100 | Harohalli sub division Kanakapura division |  | 8.73 | Supervision charges paid, MOU signed from KRDCL for self execution. BESCOM undertaking agreement process completed | work order issued from BESCOM for self execution.
[11 empty] | Ch:23+100 to 33+200 | Jigani sub division Chandapura division |  | 3.12 | Supervision charges paid, MOU signed from KRDCL for self execution. BESCOM undertaking agreement process completed | Work Order to be issued from BESCOM for self execution
5 | 3 B | Bannerghatta on SH-87 to Anekal (SH-35) via Jigani, | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 129.89 | 34.19 | 40.13 | 2019-05-06 | 104 Tree cutting proposals to be sent to concerned DFO. | Ch. 0+000 to 13+600 (Excld 6+170 to 9+160) | Jigni sub division |  | 7.8 | Supervision charges paid, MOU signed from KRDCL for self execution. | Work Order issued from BESCOM for self xecution
[11 empty] | Ch.13+600 to 18+250 | Anekal sub division |  | 7.8 | Supervision charges paid, MOU signed from KRDCL for self execution. (Excluding Anekal bypass 18+25 to 22+972) | Work Order issued from BESCOM for self execution
6 | 4A | Anekal to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield | Road | 39.28 | 312.08 | 182.23 | 106.93 | 30.2 | 2019-06-15 | 1658 Tree cutting proposals to be sent to concerned DFO. | Ch. 0+000 to 1+600 | Anekal subdivision |  | 2.46 | Intimation letter recieved on 06-12-2019 | Intimation letter issued by BESCOM on 06-12-2019. After deposition of supervision charges, BESCOM has to issue work order for self execution.
[11 empty] | Ch.1+600 to 6+500 | Attibele subdivision, (Mayasandra O & M) |  | 9 | Intimation letter recieved on 06-12-2019
[11 empty] | Ch.6+500 to 10+000 | Attibele subdivision + O&M |  | 10.45 | Intimation letter recieved on 06-12-2019
[11 empty] | Ch.10+000 to 22+000 | Attibele subdivision , Sarjapura O&M |  | 39.12 | Intimation letter recieved on 06-12-2019
[11 empty] | Ch.22+000 to 26+000 | Attibele subdivision, Sarjapura O&M |  | 8.81 | Intimation letter recieved on 06-12-2019
[11 empty] | Ch.26+000 to 31+400 | Varthur O&M (White field subdivision) |  | 8.86 | Estimate forwarded by SE to CE BESCOM | Approval of estimate for Electrical line shifting is awaited from BESCOM
[11 empty] | Ch.31+400 to 34+500 | White field O&M (White field subdivision) |  | 18.86 | Estimate forwarded by SE to CE BESCOM
[11 empty] | Ch.34+500 to 37+500 | Kadugodi O&M (whitefield subdivision) |  | 4.5 | Estimate forwarded by SE to CE BESCOM
[11 empty] | Ch.37+500 to 42+000 | Avalahalli subdivision, Sai Garden O&M |  | 6.8 | Intimation letter recieved
9 | 4 B | Construction of Elevated Corridor at Varthur village (1.300 km) | Elevated Corridor | 1.3 km Elevated corridor | 286.62 | 163.18 | 123.76 | 0 | 2019-05-20 |  | Ch.28+700 to 30+620 | Varthur |  |  | Publics objection is raised, work stopped | As per the public request proposal send to Government. After approval from the Government action will be initiated from the KRDCL
10 | 4 C | Construction of grade separators at Tally junction, | GS | GS | 133.94 | 65.17 | 68.79 | 10.35 | 2019-07-03 |  | This stretch is included in the proposal of Pkg 4A
|  | Construction of grade separators at Dommasandra junction, | GS | GS | [6 empty] | This stretch is included in the proposal of Pkg 4A
|  | Construction of grade separators at Varthur kodi junction | GS | GS | [6 empty] | This stretch is included in the proposal of Pkg 4A
|  | Construction of ROB at Kadugodi | RoB | RoB | [6 empty] | This stretch is included in the proposal of Pkg 4A
| Total |  |  |  | 1928.89 | 1138.57 | 529.09 | 288.75 | [5 empty] | 190.73
219.3

## Forest Dept (Ramanagara) (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LTD.
DETAILS OF ROADS AROUND BENGALURU PROPOSED FOR DEVELOPMENT (IN 10 PACKAGES )
Forest department | [14 empty] | Date: 28-11-2019
Sl.No | Pkg No | Name of the work | Nature of work | Length (In km) | Total project cost (In crore) | Contract amount exckluding GST | Tentative LA cost | Micelleanous and ultility shifting | Date of Site Hand over | Tree cutting as per DFR | Chainage | Range | No. of trees | Status | Action to be taken
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 8 | 12 | 4 | 5 | 6 | 7 | 8
4 | 3A | Bidadi to Jigani via Harohalli and Urgandoddi |  | 33.2 | 199.29 | 135.08 |  | 40.67 | 2019-06-20 |  | Ch. 0+000 to 4+500, 7+00 to 21+00 and 22+00 to 23+00 | Kanakapura RFO Ramnagagr ACF | 652 | > Afforestaion and development charges of Rs. 78,06,000/- remitted to DFO,Ramanagar from KRDCL. > Upset price including satutary Taxes and Charges has been paid of Rs. 10,17,039/- by the agency. | > work order to be issued from the DCF, Ramnagara to KRDCL at said amount for felling of trees as per the govt order No.FEE/168/FDP/2017 Dated:06-12-2018. > it is instructed to Agency to proceed with the felling of trees bytaking consent with the Forest Department.
|  |  | Road |  |  |  | 37.22 |  |  | 392 Tree cutting proposals to be sent to concerned DFO. | Ch. 23+000 to 33+200 | Anekal RFO Bengaluru urban ACF | 184 | > DCF (U) has been placed the proposal to the expert Committee on 19-11-2019, > it concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and action to be taken for providing land on either side of ROW for relocating Native Species trees. | Proposal to be forwarded to approval to place before experts commitee complying the observations and relaxing the provision of land required on either side of ROW for relocating the native species.
5 | 3 B | Bannerghatta on SH-87 to Anekal (SH-35) via Jigani, | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 129.89 | 34.19 | 40.13 | 2019-05-06 | 104 Tree cutting proposals to be sent to concerned DFO. | Ch.0+000 to 18+180 | Anekal RFO Bengaluru urban ACF | 520 | > DCF (U) has been placed the proposal to the expert Committee on 19-11-2019, > it concluded that Public consultation meeting to be conducted in all villages from Forest Dept in coordination with KRDCL and action to be taken for providing land on either side of ROW for relocating Native Species trees. | Proposal to be forwarded to approval to place before experts commitee complying the observations and relaxing the provision of land required on either side of ROW for relocating the native species.
6 | 4A | Anekal to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield |  | 39.28 | 312.08 | 182.23 |  | 30.2 | 2019-06-15 |  | Ch.0+000 to 25+000 | Anekal RFO Bengaluru urban ACF | 775 | proposal to be forwarded from RFO to ACF. | Proposal to be forwarded to approval to place before experts commitee for felling of trees.
[11 empty] | Ch.25+000 to 30+000 | BBMP forest Bengaluru urban ACF |  | proposal to be forwarded from RFO to ACF.
[11 empty] | Ch.30+000 to 36+500 | Mahadevapura RFO Bengaluru urban ACF | 883 | proposal to be forwarded from RFO to ACF.
|  |  | Road |  |  |  | 106.93 |  |  | 1658 Tree cutting proposals to be sent to concerned DFO. | Ch.36+500 to 42+660 | K R puram RFO Bengaluru urban ACF |  | proposal to be forwarded from RFO to ACF.

## electrical (ramanagara) (hidden)
KARNATAKA ROAD DEVELOPMENT CORPORATION LTD.
DEVELOPMENT OF ROADS AROUND BENGALURU | [15 empty] | Date: 28-11-2019
Total Length of Road 155 Km, Project cost Rs.2095 Crore
BESCOM Department
Sl.No | Pkg No | Name of work | Nature of work | Length (In km) | Total project cost (In crore) | Contract amount exckluding GST | Tentative LA cost | Micelleanous and ultility shifting cost in Cr. | Date of Site Hand over | Tree cutting as per DFR | Chainage | Division | Amount | Estimate cost in Cr. | Status | Action to be taken
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 4 | 5 |  | 6 | 7 | 8
1 | 1 | Hoskote Budigere cross (NH-4) to KIAL via Budigere | Road | 20.11 | 254 | 137.52 | 53.1 | 54.5 | 2019-07-01 | 725 Tree cutting proposals to be sent to concerned DFO | Ch. 0+000 to 8+600 | KR Puram |  | 7.2 | Pending at SE BESCOM for approval | After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate.
[11 empty] | Ch. 8+600 to 13+000 | Devanahalli |  | 3.27 | Pending at SE BESCOM for approval
[11 empty] | Ch. 13+000 to 20+100 | Yelahanka |  | 24.13 | Pending at SE BESCOM for approval
2 | 2A | Nelamangala to Madhure on SH 74 via Chikkamadhure | Road | 15.25 | 232.55 | 155.69 | 24.05 | 51.9 | 2019-04-29 | 3045 Tree cutting proposals to be sent to concerned DFO. | Ch:0+000 to 0+650 | Nelamangal O&M 1 |  | 4.42 | supervision charges deposited from KRDCL to BESCOM dated: 27-11-2019. MOU to be signed between KRDCL for self execution | Signed Under Taking for self execution & Work order to be issued from BESCOM
[11 empty] | Ch:0+650 to 8+810 | Nelamangal O&M 2 |  | 11.28 | supervision charges deposited from KRDCL to BESCOM dated: 27-11-2019. MOU to be signed between KRDCL for self execution
[11 empty] | Ch:8+810 to 15+250 | Doddaballapura |  | 3.2 | supervision charges deposited, Work order to be issued from BESCOM.
3 | 2 B | Madhure on SH 74 to Devanahalli road via Rajanukunte | Road | 23.99 | 316.3 | 169.81 | 81.05 | 61 | 2019-06-20 |  | Ch15+250 to 39+240 | Yelahanka |  |  | Electrical estimates is submitted to EE, BESCOM and Approval is awaited | After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate. MOU to be signed between KRDCL & BESCOM for self execution
4 | 2 D | ROB at Rajanakunte for crossing railway line & SH 9 AND | ROB | 1 ROB | 97.28 | 54.48 | 9.83 | 17.45 | 2019-04-04 |  | ch.31+100 to 32+630 | Yelahanka |  |  | After approval of GAD from Technical Commitee, Estimate will be submited. However estimate preparation will Progress. | Estimate will be submitted by the earliest to the BESCOM Yelahanka
|  | ROB at railway crossing at Narayanapura on MDR | ROB | 1 ROB | [6 empty] | ch.36+540 to 37+150 | Yelahanka |  | 2.8 | estimate Pprepared and submitted to BESCOM, presently at AEE | After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate. MOU to be signed between KRDCL & BESCOM for self execution
5 | 3A | Bidadi to Jigani via Harohalli and Urgandoddi | Road | 33.2 | 199.29 | 135.08 | 37.22 | 40.67 | 2019-06-20 | 392 Tree cutting proposals to be sent to concerned DFO. | Ch:0+000 to 23+100 | Harohalli sub division Kanakapura division |  | 8.73 | Supervision charges paid, MOU signed from KRDCL for self execution. | work order to be issued from BESCOM for self execution
[11 empty] | Ch:23+100 to 33+200 | Jigani sub division Chandapura division |  | 3.12 | Supervision charges paid, MOU signed from KRDCL for self execution. | work order to be issued from BESCOM for self execution
6 | 3 B | Bannerghatta on SH-87 to Anekal (SH-35) via Jigani, | Road , RoB & Grade Separator | Road 22.98km 1 Grade seperater 1 ROB | 194.11 | 129.89 | 34.19 | 40.13 | 2019-05-06 | 104 Tree cutting proposals to be sent to concerned DFO. | Ch. 0+000 to 13+600 (Excld 6+170 to 9+160) | Jigni sub division |  | 7.8 | Supervision charges paid, MOU signed from KRDCL for self execution. | work order to be issued from BESCOM for self execution
[11 empty] | Ch.13+600 to 18+250 | Anekal sub division |  | 7.8 | Supervision charges paid, MOU signed from KRDCL for self execution. (Excluding Anekal bypass 18+25 to 22+972) | work order to be issued from BESCOM for self execution
7 | 4A | Anekal to Hoskote road (NH-04) via Attibele-Sarjapura and Whitefield | Road | 39.28 | 312.08 | 182.23 | 106.93 | 30.2 | 2019-06-15 | 1658 Tree cutting proposals to be sent to concerned DFO. | Ch. 0+000 to 1+600 | Anekal subdivision |  | 2.56 | Estimate forwarded by EE to SE BESCOM on 7th Nov 2019 | After approval of the estimate, intimation letter for self execution should be communicated to KRDCL from BESCOM along with the aproved estimate. MOU to be signed between KRDCL & BESCOM for self execution
[11 empty] | Ch.1+600 to 6+500 | Attibele (Mayasandra) subdivision |  | 10.83 | Estimate forwarded by EE to SE BESCOM on 7th Nov 2019
[11 empty] | Ch.6+500 to 10+000 | Attibele subdivision |  | 11.3 | Estimate forwarded by EE to SE BESCOM on 7th Nov 2019
[11 empty] | Ch.10+000 to 22+000 | Attibele (Sarjapura) subdivision |  | 43.01 | Estimate forwarded by AEE to EE BESCOM on 25th Nov 2019
[11 empty] | Ch.22+000 to 26+000 | Attibele (Dommasandra) subdivision |  | 9.67 | Estimate forwarded by AEE to EE BESCOM on 25th Nov 2019
[11 empty] | Ch.26+000 to 36+000 | whitefield subdivision |  | 31.98 | Estimate will be submitted to EE BESCOM on 28th Nov 2019
[11 empty] | Ch.36+000 to 43+000 | Avalahalli subdivision |  | 6.83 | Estimate forwarded by EE to SE BESCOM on 11th Nov 2019
9 | 4 B | Construction of Elevated Corridor at Varthur village (1.300 km) | Elevated Corridor | 1.3 km Elevated corridor | 286.62 | 163.18 | 123.76 | 0 | 2019-05-20 |  | Ch.28+700 to 30+620 | Varthur |  |  | Publics objection is raised, work stopped | As per the public request proposal send to Government. After approval from the Government action will be initiated from the KRDCL
10 | 4 C | Construction of grade separators at Tally junction, | GS | GS | 133.94 | 65.17 | 68.79 | 10.35 | 2019-07-03 |  | This stretch is included in the proposal of Pkg 4A
|  | Construction of grade separators at Dommasandra junction, | GS | GS | [6 empty] | This stretch is included in the proposal of Pkg 4A
|  | Construction of grade separators at Varthur kodi junction | GS | GS | [6 empty] | This stretch is included in the proposal of Pkg 4A
|  | Construction of ROB at Kadugodi | RoB | RoB | [6 empty] | This stretch is included in the proposal of Pkg 4A
| Total |  |  |  | 2026.17 | 1193.05 | 538.92 | 306.2 | [5 empty] | 199.93